## Communication Plan Template - S
Communication | Method | Frequency | Goal | Owner | Audience | Others
Team Standup | WeChat | Daily | Discuss what each team member did yesterday, what they'll do today, and any blockers | Project Team | Project team
Task Progress Updates | TeamGantt | Daily | Share daily progress made on project tasks | Project Team | Project team | Ephemeral: Wechat | Preserved: Google Doc
Project Progressing Discussion | Zoom + Google Doc | Weekly | Review project status and discuss potential issues or delays. Use google doc to record the discussion. | Project Team | Project team
Project Status Report | Email | Weekly | Provide the project status to the stakeholders. Ask if there're additional requirements or modifications. | Project Team | Project team + Stakeholders | Compare against milestone
Project Milestone Review | Zoom | At milestones | Present project deliverables, showcase current features. | Project Team | Project team + Stakeholders | how to measure
Project Milestone Review | Piazza / Short Email Notice | At milestones | Gather feedback, accumulate potential customers and discuss next steps. | Project Team | Customers | Demo with Tiktok clips. | keep them inform / decision --> business strategy(coming soon.. newstuff...)
Post-mortem meeting | Meeting | At end of project | Assess what worked and what did not work and discuss actionable takeaways | Project Team | Project team
Team Members:
|  | Student ID | Email
| Chienyu Chen | 1585502 | chen.chieny@northeastern.edu
| Yihan Xu | 1566238 | xu.yihan@northeastern.edu
| Zhenyu Wang | 1375400 | wang.zhenyu1@northeastern.edu
| Ziliang Zhao | 1347572 | zhao.zili@northeastern.edu
| JingZheng Song | 1300525 | song.jingz@northeastern.edu